## Slide 1: Progress on DTT machine construction
Research Plan final meeting
DTT Consortium (DTT S.C.a r.l. Via E. Fermi 45 I-00044 Frascati (Roma) Italy)
DTT Team

## Slide 2: Vacuum vessel and ports
A1.
New call for tender to be launched within June 2024
Bellows geometry reviewed (4 types instead of 7)
The first deliverable will be a 30° sector to be used for qualification activity
Final location of support shall be finalized by the end of the mockup manufacturing when the Manufacturing readiness review will be held (about 18 months after the KoM)

## Slide 3: Frascati Coil Cold Test Facility -> CODAS
650 m2 lab Area
100 m3 large cryostat
Pumping system
FDU system
Quench detection
Control room
Cryogenic system
(LINDE Refrigerator + LN2)
TF power supply
  4.2 MVA, 42.5 kA
TF power supply delivery expected in May
FDU expected in Autumn
Cryostat in mid 2025
CODAS will invest in the preparation of the facility during SAT of the power supply and then during commissioning

## Slide 4: In-vessel coils and related power supplies
A1.
Contracts awarded to two different suppliers
KoM will be called in the next weeks
Power supplies will be delivered within the end of 2025
Conductors for in-vessel coils finalized
Conductors will be purchased this year also to perform mock-up in Building 87
Testing possible on final mock-up ADESX-U-like

## Slide 5: Divertor
Small mock-up testing completed
Interface with cooling circuit frozen
RHS requirements frozen
Expected soon:
Finalization of 3D model including toroidal shaping
Start of fabrication of the full scale mock-ups of the OVT (followed by the other PFU)
Cassette design to be finalized in order to launch call for tender

## Slide 6: Remote Manipulation Systems
A1.
HYRMAN
CMM
Contracts awarded to one single supplier
KoM will be called in the next weeks
Interfaces with divertor are frozen
Interfaces with FW could be further developed due to the finalization of the end effectors

## Slide 7: ENEA-DTT RH Training facility
Contract awarded and KoM already launched
Mockup of divertor and FW will be useful for testing alternative concepts of connections to the vessel compatible with RHS

## Slide 8: Diagnostics
Diagnostics conceptual design is under finalization
Interfaces will be locked (with cooling, ports, IVC, etc)
Engineering and procurement phase to be launched after review panel

## Slide 9: Assembly procedure
F87 preassembly hall
F185 assembly hall
F71 CS pre-assembly
Assembly contract will have the following steps:
Engineering phase (procedure, design of tooling, material);
Tooling fabrication;
Pre-assembly;
Assembly
3 buildings have been reserved for the assembly activities: F87, F71, F185

## Slide 10: Assembly procedure
F87 preassembly
Courtesy of I. Zammuto, AUG mechanical twin and winding line
F87 will be devoted to:
Qualification activities with full scale mockup;
Storage of components
Pre-assembly activities

## Slide 11: Assembly procedure
Courtesy of JT-60SA, CS pre-assembly
F71 will be devoted to:
CS Pre-assembly
Storage of components
F71 CS pre-assembly

## Slide 12: Assembly procedure
Courtesy of JT-60SA, CS pre-assembly
F185 will be devoted to:
Pre-assembly
Assembly
Storage of components
F185 assembly hall

## Slide 13
Thank you for attention
DTT Consortium (DTT S.C.a r.l. Via E. Fermi 45 I-00044 Frascati (Roma) Italy)

## Slide 14: Assembly: scope of supply
Included in assembly:
WCS
mezzanine

## Slide 15: Concluding remarks
Most of the system whose design has been developed within WPDIV is about or already under construction
Almost all interfaces have been frozen
Divertor prototype fabrication is expected to start in 2024
Assembly contract, whose tender will be launched within 2024, will guide the integration and will include a qualification phase where to test not only the assembly procedure but also the integration of many components