## Slide 1
MAG-2.1-T023-D001: CEA R&D
WPMAG Final Meeting, 12th Feb. 2020, Frascati
L. ZANI & CEA team

## Slide 2: CEA R&D on TFCNSS-1
Nb3Sn strand production & QA checks
  125 kg ordered for both Nb3Sn & Cu material
  Fabrication started in May, completion of production by WST in September 2019
  Material received by cabling company (Changtong) in December
  Production inventory received (49 unit lengths between 100 m & 700 m)
  Samples chosen (29 unit lengths of 4 meter each)
  2 samples tested for IC
Superdummy strand purchase
Objective = provide strand for cabling trials before using the Nb3Sn
  Material ordered by CEA, 208 kg produced by Luvata (stiffness adapted for cabling)
  Delivery at CEA early December 2019
  Sent to Changtong company ~ received end december 2019
Update on TFCNSS-1 fabrication

## Slide 3: WST strands tests
Actions
  November 2019: first tests in BERENICE facility: R&D WST samples
  January 2020: tests of 2 production strands
WST production strand tests
 IC ~ 330 A
Less than declared WST values
 to be checked
10 mandrels ordered to extend the measurements
He filling lines to be ordered

## Slide 4: CEA R&D on TFCNSS-1
Compaction trial
Objective = simulate the jacket compaction before acting on the definitive material
  Definitive cable dimensions set
Void fraction | 31.3 %
r1 | 2 mm
a1 | 45 mm
Jacket thickness | 5 mm
Void fraction | 40.0 %
Gap | 0.8 mm
Spiral ext. diam. | 10 mm
D2 (mm) | 66.18 mm
  Issues to procure a EU jacket at nominal dimensions (non standard)
    Will be produced in CN  OK
  Discussions with ICAS to arrange the compaction trial
    Ongoing
  A short dummy length produced by ASIPP in August (some meters) > sent to INFLPR for tomography

## Slide 5: CEA R&D on TFCNSS-1
TFCNSS-1 pieces
  Bottom Joint + Terminals
    Drawing completed
    Manufacture started (completion ~ April)
    Cable insertion tests to be conducted at CEA
  Leftover to procure
    heat treatment support
       drawing ongoing

## Slide 6: CEA R&D on TFCNSS-1
Schedule
  Compaction trials by ICAS ~ March
     To be stabilized
  Cabling trials ~ Feb - March
   To be agreed with ASIPP
  Conductor fabrication ~ April
   To be agreed with ASIPP
  TFCNSS-1 assembly at CEA ~ [May to September]
   To be consolidated
  TFCNSS-1 tests at SPC ~ October-November
   3 weeks tests targeted, to be consolidated

## Slide 7: Conclusions - perspectives
Conclusions
  TFCNSS-1 manufacture is ongoing
  Tests in SULTAN are targeted for end 2020
Perspectives TS 2020
  Extend the IC-strain tests on WST strands (check possiblities with Univ. Twente)
NB: this proposal should be adjusted according to the volume of work (when identified) which is needed for addressing Gate Review documentation

## Slide 8: Thank you for your attention Questions ?