## Slide 1: WIMAS-2 / WIMAS-4 : Planning 2020
Thomas Jonsson

## Slide 2: WIMAS-2 deliverables
Contractual Project Deliverables (WPCD reports to the Commission)
CD.D16: Tutorial, training, documentation on and release of the core-edge transport simulator in IMAS
Task Deliverables (WIMAS2 reports to the PMU)
D1: Released ETS transport simulator in IMAS with improved physics: moving boundary equilibrium, heating and current drive modules extended to synergies, testing and maintenance
D2: Verify ETS on reference ITER scenarios and report on results
D3: Provide maintenance and documentation of workflow and related tools
Project Deliverables (WPCD reports to the PMU)
WP20-CD.D02: Tutorial, training, documentation on and release of the ETS v6 transport simulator in IMAS
Milestones (WPCD reports to the PMU)
CD.M42: Released ETS transport simulator in IMAS with improved physics; e.g. moving boundary equilibrium, improved quasi-linear gyrokinetic transport model, core-edge, heating and current drive modules extended to synergies, with documentation
NOTE: We need to plan a training on Core-Edge coupling Nov/Dec 2020

## Slide 3: WIMAS-4 deliverables
Task Deliverables (WIMAS2 reports to the PMU)
D1: Demonstrate IC-Wave/Fokker-Planck consistency and wave damping on NBI ions using bi-Maxwellian representations of fast-ions in wave codes (2019)
D2: Maintain and update released heating and current drive modules (2020)
D3: Release the RABBIT code as a Kepler actor on IMAS (2020)
D4: Release of a workflow for the ECCD stabilization of NTM in IMAS (2020)

## Slide 4: Tasks to meet deliverables
1. Developing and testing actors; WF integration
  TEAM: Thomas, Nathan, Daniel, Jorge, Pär, Emil, Andreas
2. Core-edge coupling (coordinated by David Coster)
  TEAM: David, Emiliano, Rui, Thomas…
3. Moving boundary (coordinated by Jorge)
TEAM: Jorge , Daniel, Thomas…
4. ICRF-NBI synergies (PION and FoPla)
  TEAM: Mervi Matsinen, Xavier, Dani, Ernesto, Dirk, Thomas
5. Verification on ITER scenarios (coordinated by Nathan)
  TEAM: Nathan, Thomas, Michal
6. Training on core-edge
TEAM: Thomas…
NOTE: In addition we have invaluable help from Dmitriy (via CPT)

## Slide 5: Status of ETS-6 – focus on deliverables
Workflow and actors
Alpha version of ETS-6 workflow has been released
Most actors are installed, some not yet tested.
Some functionalities missing, e.g. fast ions in CP, specifying rho-grid, interpretative modes
Verification successful for: J, Te, Ti, ni
IC-NBI Synergies
PION actor not yet with synergies
FoPla actor only in CPOs
Core-edge, Moving Boundary and Verification of ITER scenarios
not yet started.
Documentation is being built gradually (inc. pages for setup, releases, how to run, physics of ETS-6, visualisation, actors docs, developers guide, verification): https://users.euro-fusion.org/iterphysicswiki/index.php/ETS-6_Documentation
To do: add ETS-6 pages in GITLAB.

## Slide 6: Status of WIMAS-4
Milestone 2019: LION with bi-Maxwellian distributions; released in 2019.
RABBIT: Good progress, but waiting for a good test case.
NTM control: TASK-PCS actor generated, but not tested.
GRAY: Merged IMAS and ITM branches, added documentation.
TORAYFOM: Progress on usage in the ETS-5 (also available in ETS-6)

## Slide 7: Identification of Key Stakeholders for WIMAS-2
INTEREST
Low
High
POWER
Low
High
Code Developers
MST/JET modellers
ITER
International collaborators
General Assembly
HRUs
MST / JET scientists (not modellers)
Stakeholders Map
JET / MST / SA TFLs
EU commission
PMU

## Slide 8: Requirement of key stakeholders for WIMAS-2
Developer / Modellers
All essential components
State-of-the-art models
Specialisation that makes ETS unique
Verified and validated models
Robust software
User friendly interface
Documentation and tutorials – easy to find, easy to understand!
General strategy for 2020
Main object is to meet deliverable.
While working towards deliverables, aim to find long term solutions aligned with requirements from Stakeholders.
EU / PMU / GENERAL ASSEMBLY:
Deliverables – critical for funding
Focus on IMAS (not CPOs)
Physics models relevant for present-day experiments, DTT, JT60-SA, ITER and DEMO
Verified and validated models
Public documentation & outreach

## Slide 9: Requirement of key stakeholders: MST 1
Dual frequency ICRF (MST)
Convective term in BgB model
Models for pedestal transport and for estimation of pedestal height
Core-SOL integration
Implementation of advanced divertor configurations
Self-consistent Fast Ion (FI) WF:
  FI impact on thermal transport + FI-driven instabilities + FI losses
  Need to integrate MEGA (EU-Japan) as 3D physics is important for MST1 (and S1)
Full integration of non-linear 3D MHD code.

## Slide 10: Requirement of key stakeholders: WEST
  Ohmic phases, study the N2 seeding impact: with heat/particle prediction and W radiation + current diffusion: #55797 (no N2) vs #55799 (with N2)
  ICRH absorption: ion vs electron heating, role of W radiation #55612
  L-H oscillating transitions: W transport/radiation through the pedestal, with interpretative pedestal, but predictive W transport/radiation, # 54719
  Long pulse modelling, explaining why no W accumulation #55787 : need LHCD module.

## Slide 11: JET 2019 requirements
H/CD workflow: NBI and ICRH heating in DT extrapolated plasmas with alpha heating (thermal,beam-target,beambeam) and neutron rate modules.
  Neutron predictions of reference existing discharges (done), but more comparisons to TRANSP with new reference shots needed
  Benchmark with JINTRAC/CRONOS/TRANSP for extrapolated DT plasmas – partly done
Current diffusion simulations (including ramp-up and rampdown, therefore evolving equilibrium and possibly with NBI and/or ICRH) – first half of 2020
TCI with TGLF/Qualikiz. Use for multi ions plasmas (H isotopes and Impurities) -Partly done, But extra efforts for benchmark are necessary
  How can ETS-6 bundle charge states?
NEO model for addressing W transport – not done
Link between ETS and H/CD (NBI and ICRH) for selfconsistent simulations – done
Models for specific edge transport requirements (pedestal pressure, pedestal density, ELMs) in order to perform true core-edge simulations – not done

## Slide 12: REQUIREMENTS, JET: New requirements in 2020
Peculiar behaviour of pedestal found in plasmas with no gas puff or pellets+gas puff
Small ELMs with high core confinement obtained with no gas puff
Compounded ELMs in pellets pacing plasmas
Pedestal density does not follow Ip.
Extreme density peaking
WPCD requirements:
Simple pedestal stability chain with self-consistent equilibrium from interpretative simulations
Gas puff models
Simple models to adjust edge particle transport
Clear splitting of D and Vn

## Slide 13: REQUIREMENTS, Modelling JT-60SA scenarios in ETS workflow
Building on previous attempts by J. Ferreira, in 2020 we propose to move towards a systematic exploitation of ETS workflow to model some JT-60SA reference scenarios and compare with previous results by other codes (CRONOS, JINTRAC)
  Proposed procedure:
Follow the ETS-RO expert guidance by submitting a web request form (first contacts ongoing). All the necessary settings for JT-60SA NBI and EC are already present.
Proposal is to start from reference full Ip Single Null inductive scenario (JT-60SA “scenario 2”).
Following step could be the study of hybrid reference scenario (JT-60SA “scenario 4.2”).
CDBM model almost ready in the latest version of ETS-5  possibility to study scenarios with ITB (JT-60SA “scenario 5”).
Data to be discussed and agreed include: equilibrium configuration, discharge phase to be modelled (current ramp-up, current ramp-down, flat-top), H&CD settings, aim of the simulation (e.g. power balance, calculation of peak ion/electron temperature / density at steady state, estimation of q profile at steady state etc.)

## Slide 14: REQUIREMENTS, WPSA: Points for discussion
Collaboration between WPCD and WPSA develops upon well established bases and some WPCD experts are already part also of WPSA team.
2020 WPSA modeling needs will/can further enhance the use of WPCD/IMAS tools in the fields of:
  MHD stability  systematic study of realistic plasmas for Initial Research Phases
  Fast ion physics  LIGKA/HAGIS IMAS integration close to completion
  Integrated scenario modelling  systematic ETS runs
  Synthetic diagnostics  longer term (EU diagnostics for JT-60SA)
  Simulation data storage under IMAS  ongoing discussion, including QST (Japan) counterpart
  Support to discharge preparation  WPSA simulator will be provided to EU users via WPCD (which can improve and customize it)
Areas of further/future collaboration could include:
  training activities for WPSA modelling collaborators to be further pushed
  data access and sharing (including requirements from F4E and QST)
  JT-60SA data mapping under IMAS (during scientific exploitation)

## Slide 15: Overview of WIMAS-2 in 2020
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
Basic solvers
Core-Edge
ITER scenarios
1 week
Code Camps/working sessions
Moving boundary
Report
2 week
Testing on ITER scenarios
Advanced solver features
HCD synergies
Training on Core-Edge
1 week
1 week
1 week
Training
We propose theses Working Sessions!

## Slide 16: WIMAS-2 Manpower
Name | ppy in 2020 | ETS devel. | Verification | Moving boundary | Core-edge | Synergies | Transport | Solver | Impurity | Nice/ Metis | Runaway | BIT1
Thomas Jonsson | 0,3 | 0,1 | 0,05 | 0,05 | 0,05 | 0,05 |  |  |  |  |  | 
Par Strand | 0,2 |  |  |  |  |  | 0,2 |  |  |  |  | 
Emil Fransson | 0 |  |  |  |  |  | 0 |  |  |  |  | 
Andreas Gillgren | 0,1 |  |  |  |  |  | 0,1 |  |  |  |  | 
David Coster | 0,05 |  |  |  | 0,05 |  |  |  |  |  |  | 
Emiliano Fable | 0,1 |  |  |  | 0,1 |  |  |  |  |  |  | 
Bruce Scott | 0,05 |  |  | 0,05 |  |  |  |  |  |  |  | 
Albert Gutiérrez | 0 |  |  |  |  | 0 |  |  |  |  |  | 
Mervi Mantsinen | 0,1 |  |  |  |  | 0,1 |  |  |  |  |  | 
Xavier Saez | 0,3 |  |  |  |  | 0,3 |  |  |  |  |  | 
Ignacio Lopez | 0 |  |  |  |  | 0 |  |  |  |  |  | 
D. Van Eester | 0,2 |  |  |  |  | 0,2 |  |  |  |  |  | 
Ernesto Lerche | 0,2 |  |  |  |  | 0,2 |  |  |  |  |  | 
Dragan Poljak | 0,05 |  |  |  |  |  |  | 0,05 |  |  |  | 
Silvestar Šesnić | 0,05 |  |  |  |  |  |  | 0,05 |  |  |  | 
Vicko Dorić | 0,05 |  |  |  |  |  |  | 0,05 |  |  |  | 
Anna Šušnjara | 0,05 |  |  |  |  |  |  | 0,05 |  |  |  | 
Irena Ivanova-Stanik | 0,3 |  |  |  |  |  |  |  | 0,3 |  |  | 
Michal Poradzinski | 0,1 |  | 0,1 |  |  |  |  |  |  |  |  | 
Soma Olasz | 0,1 |  |  |  |  |  |  |  |  |  | 0,1 | 
Gergo Pokol | 0 |  |  |  |  |  |  |  |  |  | 0 | 
Jorge Ferreira | 0,4 | 0,1 | 0,05 | 0,15 | 0,1 |  |  |  |  |  |  | 
Rui Coelho | 0,1 |  |  |  | 0,1 |  |  |  |  |  |  | 
Nathan Cummings | 0,5 | 0,2 | 0,3 |  |  |  |  |  |  |  |  | 
Daniel Dumitru | 0,5 | 0,3 |  | 0,1 | 0,1 |  |  |  |  |  |  | 
David Tskhakaya | 0,3 |  |  |  |  |  |  |  |  |  |  | 0,3
Cedric Boulbe | 0,1 |  |  |  |  |  |  |  |  | 0,1 |  | 
Jean-François Artaud | 0,1 |  |  |  |  |  |  |  |  | 0,1 |  | 
Blais Faugeras | 0,2 |  |  |  |  |  |  |  |  | 0,2 |  | 
22 | 4,5 | 0,7 | 0,5 | 0,35 | 0,5 | 0,85 | 0,3 | 0,2 | 0,3 | 0,4 | 0,1 | 0,3
Additional resources
Dmitriy (CPT, time allocated)
Denis (PMU, no allocation)

## Slide 17: WIMAS-4 manpower
Name | Workplan | ppy in 2020
Thomas Jonsson | Task coordination; contribute to D1; contribute to D2; contribute to D3 | 0,35
Jari Varje | Completing the development and IMAS adaptation of the RFOF-ASCOT actor for NBI-ICRH simulations coupled to wave actors | 0
Seppo Sipilä | Completing the development and IMAS adaptation of the RFOF-ASCOT actor for NBI-ICRH simulations coupled to wave actors | 0,1
Markus Weiland | Adaption of the fast, high-fidelity NBI solver RABBIT for IMAS | 0,1
Roberto Bilato | Contribute to the release of ETS transport simulator in IMAS with focus on TORIC | 0,1
Albert Gutiérrez | Development of High Performance Computing capability for fusion workflows, integrated to the ITER Modelling framework | 0
Mervi Mantsinen | contributing with the ICRF code PION to the deliverable D1,D2 | 0
Xavier Saez | contributing with the ICRF code PION to the deliverable D1,D2 | 0
Daniel Gallart | contributing with the ICRF code PION to the deliverable D1,D2 | 0
Ignacio Lopez | contributing with the ICRF code PION to the deliverable D1,D2 | 0
D. Van Eester | CYRANO (wave), TOMCAT (wave) and STIXREDIST (Fokker-Planck) actors, all working with CPO and IDS structures. | 0
Ernesto Lerche | CYRANO (wave), TOMCAT (wave) and STIXREDIST (Fokker-Planck) actors, all working with CPO and IDS structures. | 0
Silvana Nowak | Release of an IMAS workflow for the ECCD stabilization of NTM (2020) | 0,2
Lorenzo Figini | Maintain and update the GRAY module (2019). Release of an IMAS workflow for the ECCD stabilization of NTM (2020) | 0,2
Egbert Westerhof | Maintenance of the IMAS based versions of TORAYFOM and RELAX and support to users and possibly the use of these codes for MSTs. | 0,1
Soma Olasz | Contribute to the maintenance and update of released runaway physics modules | 0
Gergo Pokol | Contribute to the maintenance and update of released runaway physics modules | 0
Laurant Villard | Maintenance of the Lion module | 0,05
18 |  | 1,2

## Slide 18: Listing smaller sub-tasks
A list of tasks has been generated https://docs.google.com/spreadsheets/d/1Ps-cGQyKNsYTObCr5Kqu58bXBNQdH45Fjpz5QD0hLB0/edit?usp=sharing
Focus on Feb. 2020:
  Verification
  Missing actors and integration features
  Visualisation
Before end of 2020:
  Training/documentation (Commission deliverable)
  Edge-core (Commission deliverable)
  Synergies (Task Deliverable)
  Moving boundary (Task Deliverable/Milestone)
  ITER-verification (Milestone)
NR | Deliverable | Category | Description | Assigned to | Priority | Deadline | Status
1 |  | Verification | TCIanalytics should be tested for a simple test case (it is not yet working). I suggest the latest ETS-6, load the param file for the Te benchmark and add TCI-analytics (AdditionalTransport = On). Make sure that the core_transport IDS includes D_Te and V_Te from TCI-analytics. Keep it simple, e.g. D_Te=1 and V_Te=0. Make sure to run more than one time step. | Dmitriy | HIGH | feb | On going
2 | pre-core-edge | Verification | ETS-5 benchmarks 1: Current diffusion with NCLASS, inc. bootstrap currents. | Dmitriy | HIGH | soon | On going
3 | pre-core-edge | Verification | ETS-5 benchmarks 2: Te/Ti with anomalous transport coefficients | Dmitriy | HIGH | feb | Te ok, Ti ongoing
4 | pre-core-edge | Verification | ETS-5 benchmarks 3: ne/ni(1spec)/ni(2spec) with anomalous transport coefficients + quasineutrality settings | Dmitriy | HIGH | feb | 
5 | pre-core-edge | Verification | ETS-5 benchmarks 4: Test NBI sources | Dmitriy, Daniel, Nathan | HIGH | feb | On going. Need EWE input
6 | pre-core-edge | Verification | ETS-5 benchmarks 5: Test ICRH sources |  | HIGH | soon | 
7 | pre-core-edge | Verification | ETS-5 benchmarks 6: Test ECRH sources |  | HIGH | soon | 
8 | pre-core-edge | Verification | ETS-5 benchmarks 7: Te/Ti with sources |  | High | soon | 
9 | pre-core-edge | Verification | ETS-5 benchmarks 8: ne/ni(1spec)/ni(2spec) with sources |  | High | soon | 
10 |  | Development | Actor for database sources (release source code, verification, documentation) | Thomas | High | feb | Actor released, tests are ok
11 |  | Development | Actor for database transport coefficients (release source code, verification, documentation) | Thomas,Daniel,Dmitriy | High |  | 
12 |  | Development | Actor for interpretative core-profiles (release source code, verification, documentation) | Thomas,Daniel,Dmitriy | High |  | Ongoing
13 |  | Development | Actor for analytical sources (release source code, verification, documentation) |  | Medium |  | 
14 |  | Development | Adjust J-parallel to boundary condition when the equilibrium changes. First in ETS-5, then in ETS-6. |  | Medium |  | 
15 |  | Development | Adjust density for when the equilibrium is changing. |  | Low |  | 
16 |  | Development | Adjust temperature for when the equilibrium is changing. |  | Low |  | 
17 |  | Development | Add new radial grid; implemented it in ETS-init? | Dmitriy | Low |  | 
18 | ITER scenarios | Verification | Set up simple test cases for ITER scenarios | Nathan,Thomas | HIGH | july | 
19 | ITER scenarios | Verification | ITER verfication of transport models. Create test cases for each equation ne, ni, Te, Ti, J and each relevant model (BgB, EDWM, QLK, TGLF, NCLASS). Documentation. If possible, build automated tests. | Nathan,Thomas | HIGH | aug | 
20 | ITER scenarios | Verification | ITER verfication of sources. | Nathan,Thomas | HIGH |  | 
21 | ITER scenarios | Verification | ITER verfication of current evolution. | Nathan,Thomas | HIGH |  | 
22 | ITER scenarios | Verification | ITER verfication of temperature evolution | Nathan,Thomas | HIGH |  | 
23 | ITER scenarios | Verification | ITER verfication of density | Nathan,Thomas | HIGH |  | 
24 |  | Visualisation | Visualisation: Add more info in viz/ETSplugin; add panels for transport, sources - more requests needed | Dejan, Nathan | High | spring | 
25 | >2020 | Development | Add Irenas impurity code to workflow |  | Low | 2021 | 
26 | >2020 | Verification | Impurities, simple benchmark with ETS-5 |  | Low | 2021 | 
27 |  | Development | Implement internal boundary condition (first in ETS-5 and then ETS-6) |  |  |  | 
28 |  | Development | Add logging information option in both ETS-5 and ETS-6 transport-solvers | Dmitriy,Thomas | Need for ni | soon | 
29 | Extended ETS | Development | Moving boundary equilibrium (as in deliverable) |  | HIGH | dec | 
30 | Extended ETS | Development | NBI-IC synergies with PION. | Mervi, Ignacio, Xavier | HIGH | sept | 
31 | Extended ETS | Development | NBI-IC synergies with FoPla. | Dirk, Ernesto | HIGH | sept | 
32 |  | Development | Add BgB into the ETS-6 |  | Medium |  | 
33 | >2020 | Development | Tool to populate Scenario IDS |  | Low |  | 
34 | Core-edge/training | Release | Set up structure for releasing dressed Keplers, workflows and the ETS-gui. |  | High |  | 
35 | >2020 | Theory | Formulate momentum equations |  | Low | 2021 | 
36 | >2020 | Development | Implement momentum equations |  | Low | 2021 | 
37 | >2020 | Verification | Benchmark against similar transport code |  | Low | 2021 | 
38 | >2020 | Development | Add instantaneous events |  | Low | 2021 | 
39 | Core-edge/training | Doc | Write documentation |  | High | dec | 
40 | Core-edge/training | Doc | Write tutorial |  | High | dec | 
41 | pre-core-edge | Verification | Test convergence loop |  | High |  | 
42 |  | Development | Saving first time-step |  | Medium |  | 

## Slide 19: Core-edge integration, sub-tasks
List of possible tasks (proposal from Thomas, to be discussed with the team)
PLANNING: Clarify what we want the edge code to predict, the design the core-edge interface etc. One important early decision to make is if we go with SOLPSz1, or a code similar what’s been implemented in ASTRA. I do not think we’ll have time or manpower to do more than one edge-code.
PROGRAMMING: We need an edge-code that outputs the core_profiles and possible some other IDS. This could be e.g. SOLPSz1 or perhaps something similar to what’s implemented in ASTRA.
PROGRAMMING: We need a code that maps data from the edge_profiles IDS into a transport_solver_numerics IDS. The output should be used by the core-transport-solver.
PROGRAMMING: We need a code that maps a core_profiles IDS from the core-transport-solver into boundary conditions for the edge-code.
INTEGRATION: Kepler implementation of this coupling.
INTEGRATION: We need to assess our data-needs. Do we need new data from EWE? Do we need other types of preprocessing tools? Perhaps we need an update to ets-init actor to initialise edge_profiles IDS and edge-numerics?
VISUALISATION: We need to be able to assess our results and compare with references. This could be done in viz, or perhaps through simple python script.
TESTING: We need some form of low-level testing of T1-T3 to make sure these components work as they should. Thus we need reference data to compare that can be reproduced by the codes with high precision - for easy testing. I would suggest that we do not do this low-level test in Kepler.
TESTING: Once we have the full workflow running we need a complete test case. Again we need data that we can reproduce with high precision using the ETS-6 workflow. If we could set up a case with ETS-5 and SOLPSz1, this would be ideal since the two codes are very similar and we’ll anyway compare the core-solvers against ETS-5! If we try something from ASTRA, then I’m afraid that we first need a careful benchmark of the core-solver before we can even start considering that we would be able to reproduce the ASTRA results with core-edge, something we probably don’t have time for this year.

## Slide 20: Core-edge integration, constraints and time-line
List of possible constraints (proposal from Thomas, to be discussed with the team)
In my view we need to start thinking low-level testing, Task (T8), from day one.
The three programming Tasks (T2-4) could be done in parallel (assigned to different people).
For Integration Task T5 we need to have actors from T2-4 before we can do anything practical. I’d like to sketch a design already early on (perhaps in Risø). We could also try to generate some dummy actors fairly early to avoid blocking T5.
The full workflow testing, T9, has to be done in steps, turning on different features one at a time. This requires planning and will take time. I’d like to start this work as early as possible - perhaps during the summer, or early autumn.
The training should probably be scheduled for late November or Early December. This means that we need some intensive weeks of Code Camping leading up to this event. Proposal: one week in September, one in October and one in November.
WIMAS-2 has several other very challenging tasks to complete in 2020. Thus, man power may be diverted in different direction in order to deliver something needed by someone else. Thus, we need margins in a our planning and we need to get things started asap.
We need a early assessment of the manpower required to do this work. The three main people involved (Dave, Rui, Emiliano) have only 0.25 ppy allocated, so we’ll need to bring in people with less experience to do a large fraction of this work.

## Slide 21: Moving boundary
Plan is to enable a prescribed moving boundary - not mean free boundary.
Thus, the ETS has to be able to handle compression.
We believe all required features are already implemented (thanks to Denis).
The focus is on testing and debugging.
Time-line:
No detailed plan. We need testing to see how much work is required.
Start during the spring.
The goal is to complete this task before the end of the summer.

## Slide 22: Synergies
Options for 2020 deliverable:
PION
FoPla
ASCOT-RFOF (require HPC, so primarily an advanced )
Time plan:
Spring: adaptation and developing actors.
Summer: Integrate alpha-version into ETS-6.
Autumn: Release of stable version.

## Slide 23: Verification on ITER Scenarios
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
Data from ITER
Ids2cpo, for ETS-5
Verification of sub-WFs
1 week
Code Camps/working sessions
Document Provenance
Report
2 week
Scenario verification
Sufficient input for ETS
Design verification param-files
1 week
1 week
1 week
Training
We propose theses Working Sessions!

## Slide 24: Verification on ITER Scenarios
Verification of ITER Scenarios - run both ETS-6 and ETS-5
  Receive data from ITER (spring)
  Detailed documentation of provenance for all data used.
  Ensure that the ETS can ran with the input data from ITER. In case data-field is missing, report to data-providers.
  Translate data into CPOs for ETS-5. Make sure ids2cpo provides the complete mapping needed by ETS-5.
  Design verification param-files for equivalent ETS-5 and ETS-6 runs.
  First compare minor sections of the ETS-6 workflow
  Validate entire scenarios; validation “ETS-5 vs ETS-6” and “ETS-6 vs ITER-reference”.
  Write a report on the results.
Time plan:
1-4 spring
5, start in spring, end in summer
6 summer
7-8 autumn

## Slide 25: Timeline for 2020 deliverable: Core-edge
 | Jan-Apr. | May-July | Aug-Sept | Oct-Dec
Coster |  |  |  | 
Emiliano |  |  |  | 
Rui |  |  |  | 

## Slide 26: Timeline for 2020 deliverable: Moving boundary
 | Jan-Apr. | May-July | Aug-Sept | Oct-Dec
Jorge | Moving boundary | Moving boundary Core-edge | Moving boundary Verification | Training
Daniel | 30-40% WIMAS-2 Database actors Workflow development Verification Moving boundary | 50% WIMAS-2 Moving boundary Workflow development Verification | 60-70% WIMAS-2 Moving boundary Workflow development Verification | 60-70% WIMAS-2 Training Verification

## Slide 27: Timeline for 2020 deliverable: Verification on ITER scenarios
 | Jan-Apr. | May-July | Aug-Sept | Oct-Dec
Nathan | Verification Receive data from ITER. Document data provenance. Ensure data is complete. Translate data into CPOs. Design param-files. cpo2ids: Development/support Visualisation: Learn to add plots in viz/ETS | Verification Verification of sub-WFs Visualisation: Support for viz/ETS | Verification Verification of sub-WFs Scenarios verification Visualisation: Support for viz/ETS | Verification Scenarios verification Write report. Visualisation: Support for viz/ETS
Michal | Verification Design param-files. | Verification Verification of sub-WFs | Verification Verification of sub-WFs Scenarios verification | Verification Scenarios verification Write report.

## Slide 28: Timeline for 2020 deliverable: IC-NBI synergy
 | Spring | Summer | Autumn
Dirk/Ernesto | Maintenance and development when time permits. | Develop and release IMAS actor of FoPla. | Maintenance and development when time permits.
Mervi/Xavier/Dani | Add NBI interface. Verification. | Deliver alpha version. Verification and debugging. | Deliver stable version

## Slide 29: Timeline for 2020: H&CD and NTM Control
 | Spring | Summer | Autumn
Lorenzo | Maintenance for GRAY. Developing TASK-PCS for NTM control. | Maintenance for GRAY. Developing TASK-PCS for NTM control. | Maintenance for GRAY. Developing TASK-PCS for NTM control.
Silvana | - | Create a new version for the NTM module in ETS translating from CPO to IDS . | IMAS workflows for the stabilisation of NTM with ECCD for the deliverable D4.
Seppo |  |  | 
Markus |  |  | 
Laurent Villard |  |  | 

## Slide 30: Timeline for 2020: Transport and solver
 | Jan-Apr. | May-July | Aug-Sept | Oct-Dec
Pär | TCI-maintenance | TCI-maintenance | TCI-maintenance | TCI-maintenance
Emil, Andreas | Verification of transport actors | Verification of transport actors | - | -
Bruce | Maintenance BgB/NEOWES | Maintenance BgB/NEOWES | Maintenance BgB/NEOWES | Maintenance BgB/NEOWES
 | Spring / summer | Autumn + 2021
Dragan, Anna, Vicko, Silvestar | Create new FEM solver with modified weak form (to avoid derivatives of D) | New FEM solver with modified space-time discretisation (first space and then time discretisation)

## Slide 31: Timeline for 2020: Neutrals, impurities, BIT1, METIS, NICE
 | Jan-Apr. | May-July | Aug-Sept | Oct-Dec
Irena | Discussion about boundary condition in IMAS for neutrals. Prepare initial ids for neutrals. | Start work on solver for neutrals | Finish solver for neutrals | Testing the solver for neutrals
Tskhakaya |  |  |  | 
Cedric |  |  |  | 
Jean-Francois | Integrated modelling for WEST | Integrated modelling for WEST | Integrated modelling for WEST | Integrated modelling for WEST
Blais |  |  |  | 
 | March | June | Dec
Gergo/Soma | Integrate Runaway Indicator into ETS6 Instantaneous events. Till the end of the ITER Code Camp | Integrate Runaway Fluid into ETS6 H&CD workflow. Till the end of summer Code Camp. | Integrate kinetic runaway electron modelling into ETS6. Till the end of the year.

## Slide 32: Timeline for 2020: WIMAS-2 Coordination
2020 Timeline for Task EWE-5
 | March | April | May | June | July
Thomas Jonsson | Workflow develop Verify H&CD actor Verify convergence loop Core-edge Planning meetings Moving boundary Planning meetings H&CD synergies Integrate FoPla-WF in ETS-5 Verification ITER Data from ITER/Metis | Workflow devel tbd Core-edge tbd Moving boundary tbd H&CD synergies tbd Verification ITER tbd | Workflow devel tbd Core-edge tbd Moving boundary tbd H&CD synergies tbd Verification ITER tbd | Workflow devel tbd Core-edge tbd Moving boundary tbd H&CD synergies tbd Verification ITER tbd | Partly vacation

## Slide 33: Timeline for 2020 : WIMAS-2 Coordination
2020 Timeline for Task EWE-5
 | Aug | Sept | Oct | Nov | Dec
Thomas Jonsson | 1 week conference Workflow devel tbd Core-edge tbd Moving boundary tbd H&CD synergies tbd Verification ITER tbd | Workflow devel tbd Core-edge tbd Moving boundary tbd H&CD synergies tbd Verification ITER tbd | Workflow devel tbd Core-edge tbd Moving boundary tbd H&CD synergies tbd Verification ITER Tbd Training Prepare training | Core-edge Finalise Moving boundary Remaining issues H&CD synergies Finalise Verification on ITER scenarios Final simulations Start report Training Prepare training | Core-edge Remaining issues Moving boundary Remaining issues H&CD synergies Remaining issues Verification ITER Finalise report Training Give training session