## Slide 1: Summary and plans for the WDEV area
M. Romanelli

## Slide 2: WDEV - Area
Reduced from 3 tasks in 2019 to 2 tasks in 2020
WDEV-1 Linear MHD stability chain for energetic particles and non-linear codes for fast-ion MHD interaction
WDEV-2 Free Boundary Equilibrium and feedback control
-> 2020 D4 deliverable moved to WIMAS-2: Release of a version of the prototypes FBE and advanced transport simulator workflow usable for general cases and ready to be deployed in JET/MST/WPs.
WDEV-3 / TSVV Advanced transport models for pedestal / edge
D2: (2020) Develop and test (in ETS) reduced edge/pedestal turbulent transport models
This deliverable has been included in the TSVV task
LH transition and pedestal physics

## Slide 3: Plans for WDEV-1
Team 1: C. Di Troia, F. Napoli
Team 2: S. Briguglio, G. Fogaccia, G. Vlad
Team 3: R. Coelho, P. Rodrigues
 | Jan | Feb | Mar | Apr | May | Jun
Team 1 | Read numerical distribution function from IMAS /IDS |  |  |  |  | 
Team 2 | Make HYMAGYC IMAS compliant (IDS I/O) |  |  |  |  | 
Team 3 | Make CASTOR-K IMAS compliant |  |  |  |  | 
Task Completed by the Eindhoven Code-Camp (June)
Start validation exercise against other IMAS workflows (LIGKA, HALO) on same input IDSs (including fast ion distribution IDS). This require establish contact with ITER and the LIGKA, HALO teams
 | Jul | Aug | Sep | Oct | Nov | Dec
Team 1 |  |  | Provide GUI for users |  |  | 
Team 2 |  |  | Insert HYMAGYC in the MHD-EP workflow |  |  | 
Team 3 |  |  | Insert CASTOR-K in the MHD-EP workflow |  |  | 
MHD-EP workflow released by end of year code camp
Dedicated WDEV-1 working session scheduled for the last week of October

## Slide 4: WDEV-2 2020 deliverable in WIMAS-2
Team 1: C. Boulbe, J-F Artaud
Team 2: B. Faugeras, C. Boulbe, J. F. Artaud WIMAS-2 team
 | Jan | Feb | Mar | Apr | May | Jun
Team 1 | Complete tests on the Nice – Metis workflow with controllers |  |  |  |  | 
Team 2 | Prepare Nice – ETS workflow with controllers based on Nice – Metis coupling algorithm |  |  |  |  | 
Task Completed by the Eindhoven Code-Camp (June)
 | Jul | Aug | Sep | Oct | Nov | Dec
Team 1 |  |  | Benchmark Nice – Metis with Nice - ETS |  |  | 
Team 2 |  |  | Release the Nice – ETS workflow with controllers |  |  | 
MHD-EP workflow released by end of year code camp

## Slide 5: WDEV-3 / TSVV
Team 1: TSVV team, James Martin Collar
Team 2: P. Strand, E. Fransson
 | Jan | Feb | Mar | Apr | May | Jun
Team 1 | Provide an analytic transport model (BgB like) for the ETB region based on GK analysis results |  |  |  |  | 
Team 2 | Enable the use of an analytic model in the ETB domain of ETS-5 / ETS-6 and implement the epsilonBgB model |  |  |  |  | 
Task Completed by the Eindhoven Code-Camp (June)
 | Jul | Aug | Sep | Oct | Nov | Dec
Team 1 |  |  | Refine the model based on new results and ETS tests |  |  | 
Team 2 |  |  | Release transport model in ETS-5 / ETS-6 for users to validate |  |  | 
ETB transport model released by end of year code camp

## Slide 6: Plans for 2020
Identification of Key Stakeholders for the WDEV area
INTEREST
Low
High
Power
Low
High
MST/JET users
ITER
International collaborators
General Assembly
JET / MST TFLs PLs
HRUs
MST / JET scientists (not users)
Stakeholders Map