## Slide 1: DTT diagnostic equipment: design progress status
A.Murari 2,4 , L.Gabellieri 1,3 and M.A.Caponero3, D.Fiorucci3, O.Tudisco1,3
DTT S.c.a r.l Frascati (Italy)1, Consorzio RFX Padova (Italy)2, ENEA Fusion and Nuclear Safety Department, Frascati (Italy)3, Istituto per la Scienza e la Tecnologia dei Plasmi, CNR, Padova, Italy4
WPDIV-IDTT 2023 Midterm meeting - 17–19 July 2023 ENEA Frascati

## Slide 2: OUTLINE
WPDIV-IDTT Diagnostic Area design activities
DTT Diagnostic Equipment: strategy for diagnostic implementation
Design Activities goals
Planning priorities
DAY-0 equipment: requirements and next steps
Diagnostic suites for specific and transversal studies
Issues
S6 session agenda

## Slide 3: 2023 WPDIV IDTT Divertor Diagnostics Area design activities
DIV-IDTT.S.06 | Proposal Title / Task Title | Project Leader (THM-DIA) | Deliverable Owner | DTT Shareholders | EU Institutions | DTT Funct. Budg. (PM) | WPDIV (PM)
T021 | Bolometry and SXR Tomography, SXR imaging | DTI - G.M.Apruzzese (ENEA) | G.M.Apruzzese (ENEA), F.Bombarda (ENEA), D.Pacella (ENEA) | ENEA,I NFN, RFX,ISTP-CNR, UNIMIB, UNITOV |  | 1,0 | 18,8
T022 | Interferometers and Polarimeters | DIP - D.Fiorucci (ENEA) | D.Fiorucci (ENEA), F.Filippi (ENEA), A.Fassina (ENEA), P.Gaudio (UNITOV), M.Alonzo (ENEA) | ENEA, RFX, UNITOV |  | 2,0 | 12,0
T023 | Active and Passive Spectroscopy | DSP - F.Bombarda (ENEA) | F.Bombarda (ENEA) | ENEA, RFX, POLITO, UNIMIB |  | 2,0 | 15,5
T024 | Neutrons and Gammas | DGN - D.Marocco (ENEA) | D.Marocco (ENEA) | ENEA,I STP-CNR, POLITO, UNIMIB |  | 3,0 | 23,4
T025 | Magnetics Sensors | DMA - G.Artaserse (DTT), M.Baruzzo (ENEA) | G.Artaserse (DTT), M.Brombin (RFX), G.Sias (UNICA), A.Pironti (CREATE), I.Duran (IPP-Prague) | ENEA, CREATE, RFX, UNITUS, CETMA | IPP-Prague | 2,0 | 66,0
T026 | Embedded, IR/VIS cameras and PWI Diagnostics | DWI - M.Iafrati (ENEA) | M.Iafrati (ENEA), M.Alonzo (ENEA), M.Agostini (RFX), M.Spolaore (RFX), S.Almaviva (ENEA), L.Laguardia (ISTP-CNR), M.Caponero (ENEA), M.Houry (CEA-Cadarache) | ENEA, RFX,I STP-CNR | CEA-France | 1,25 | 33,3
T027 | ECE Diagnostics | DEE - S.Schmuck (ISTP-CNR) until 31/05/23 | S.Schmuck (ISTP-CNR), W.Bin (ISTP-CNR) | RFX, ISTP-CNR |  | 4,00 | 11,0
T028 | Reflectometry | DRE - G.De Masi (RFX) | G.De Masi (RFX) | ENEA, INFN,RFX |  | 1,00 | 9,0
T029 | Thomson Scattering Systems | DTS - L.Giudicotti (RFX) | L.Giudicotti (RFX) | ENEA, RFX |  | 2,00 | 5,0
T030 | Run Aways Diagnostics | DRA - B.Esposito (ENEA) | B.Esposito (ENEA), M.Hoppe (VR-KHT) | ENEA, CREATE, UNITOV | VR-KHT-Sweden | 2,50 | 5,9
T031 | Fast Particles Diagnostics | DFP - M.Nocente (UNIMIB) | M.Nocente (UNIMIB), M.G.Munoz (Univ. de Sevilla) | ISTP-CNR, UNIMIB | Univ. de Sevilla | 1,00 | 8,0

## Slide 4: DTT Diagnostic Equipment: Strategy for diagnostic implementation
DTT DIAGNOSTIC EQUIPMENT : ABOUT #80 DIAGNOSTIC TECHNIQUES
DAY-0 PHASE 1 | Machine and divertor protection & plasma control | ~30
 | Science program (Phase 1)  TBD | 0
DAY-2  PHASE 2 | Science program (Phase 2)  TBD | ~50
Day-0 Day-2 Day-4
Good diagnostics coverage in relation to the DTT experiment mission  guess an optimizable as well as complete, diagnostic equipment
In addition to DAY0 equipment, a number of advanced diagnostic systems is anyway being conceived until now to assess interface and integration issues
The design activities of the DTT equipment, as currently planned, were only started this year 2023 and currently in progress as stated in the 11 DTT Diagnostic Proposals

## Slide 5: THM-DIA 2023 Design Activities goals
DAY-0 diagnostic equipment and DAY-2 diagnostic equipment (parts linked to the assembly planning) :
  Finalise Conceptual design (final assessment of interface and integration, remote handling, cooling, vacuum etc …)
  Preliminary estimation of costs (to assess DAY-0 equipment)
  Activity Planning definition (scheduling of Procurement, Assembling and Commissioning phases) (to define dagnostic planning)
DAY-2 diagnostic equipment
Progress on Preliminary Conceptual Design (finalizing allocation, interface and integration, remote handling, cooling, vacuum issues & requirements etc…)

## Slide 6: THM-DIA 2023 activities planning priorities
PRIORITIES of the activities have to be aligned to:
machine assembly planning and critical lines of the project
… WHAT IS MORE URGENT TO BE FINALIZED FOR THE PROGRESS of Diagnostic design activities ?
Alignment of the main machine CAD design to the current state of progress of Divertor Cassette, First Wall Outer/Inner design etc...
Completion of Port plug design (RH rails design assessment etc …)
Vacuum Allowed Materials, Baking etc… requirements assessment
Diagnostic positioning  link conditioning, impact on Assembly planning | Diagnostic positioning / planning link conditioning | Diagnostic Assembly Activities
1 | External Vacuum Vessel | 2026
2 | Internal Vacuum Vessel | 2027
3 | DIVERTOR instrumentation | 2026 - 2027 (tbc)
4 | Outer/Inner First Wall | 2027 (tbc)
5 | Others DAY-0 Diagnostics | 2028

## Slide 7: DAY-0 equipment requirements and next steps
 | WHAT | WHO | WHEN
1 | Validation of DAY-0 equipment adopted strategy | DTT-TCM activities | … discussion in progress …
2 | Cost estimate | 2023-THM-DIA Proposal | End 2023
3 | Definition of Phase 1 Science Program | Research Plan activities | …waiting for …
… NEXT STEPS to finalize the DAY-0 equipment strategy:
THM-DIA DataBase | Port, Sector | Inside- Cryostat |  |  |  | Vacuum | Outside - Cryostat | Remote Handling activities | Cabling & Routing | Phase1 (Day-0) / Phase2 (Day-2) |  | 
 |  | Ex /In VV | Out/In FW | IVT/CT/OVT Divertor | Port Plug | Window - Feed Trough |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | Protection (machine & divertor) | Essential for operation | Science program
LINK DTT2023 _04165 | Allocation | Descriptions & Requirements |  |  |  |  |  |  |  | Measurement descriptions and classification |  | 
This document is updated continuously day after day

## Slide 8: Diagnostic suites for specific and transversal studies
Diagnostic Equipment for detachment studies and control
Divertor instrumentation: protection and studies
Runaways protection and studies Equipment (including SPI)
Diagnostics for neutral particle profiles
Stray radiation…

## Slide 9: Critical points
Dramatic lack of resources: teams very thin on the ground and heavy bureaucratic and organisational burden.
One PL resigning in May and two retiring very soon (both in autumn): strategy to be defined.
Three ROs not available next year: strategy to be defined.
Planning DTT: some diagnostic activities with very tight schedule.
Research plan: priorities to be defined.
Laboratories: availability required soon
Matrix organisation of the diagnostics: required coordinators for diagnostics essential for protection and scientific priorities

## Slide 10: WPDIV-IDTT Midterm Meeting 2023
S6 - Diagnostics Tuesday 18th July 13:30-17:00 |  | 
Duration | Speaker | Title
00:15 | Andrea Murari | DTT diagnostic equipment: design progress status
00:10 | Questions | 
00:25 | Giovanni Artaserse | DTT Magnetic Sensors equipment: design progress status and planning
00:10 | Questions | 
00:25 | Matteo Iafrati | DTT InfraRed and Visible cameras, Langmuir Probes and Thermocouples equipment: design progress status
00:10 | Questions | 
00:30 | Break | 
00:25 | Francesca Bombarda | DTT spectroscopy equipment essential for machine operation and detachment studies: design progress status
00:10 | Questions | 
00:25 | Donatella Fiorucci | Interferometers/Polarimeters equipment essential for machine operation and detachment studies: design progress status
00:10 | Questions | 
00:15 | Discussion & Conclusion | 

## Slide 11
DTT diagnostic equipment: design progress status
WPDIV-IDTT 2023 Midterm meeting - 17–19 July 2023 ENEA Frascati
A.Murari 2,4 , L.Gabellieri 1,3 and M.A.Caponero 3, D.Fiorucci 3, O.Tudisco 1,3
DTT S.c.a r.l Frascati (Italy)1, Consorzio RFX Padova (Italy)2, ENEA Fusion and Nuclear Safety Department, Frascati (Italy)3, Istituto per la Scienza e la Tecnologia dei Plasmi, CNR, Padova, Italy4