## DMA Planning 2023
|  | Project Start Date: | 2023-01-02
|  | Project Name: | THM-DIA-DMA
|  | Project Leader | G.Artaserse/M.Baruzzo | [7 empty] | 2023-01-02 | [12 empty] | 2023-01-02 | [12 empty] | 2023-01-02 | [12 empty] | 2023-01-02
[11 empty] | 2023-01-09 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-13 |  |  |  | 2023-04-10 |  |  |  | 2023-05-08 |  |  |  |  | 2023-06-12 |  |  |  | 2023-07-10 |  |  |  |  | 2023-08-14 |  |  |  | 2023-09-11 |  |  |  | 2023-10-09 |  |  |  |  | 2023-11-13 |  |  |  | 2023-12-11 | [5 empty] | COMMENTS
Week starting: | time axis 2023-01-02 to 2023-12-25
Item # | Task # | Task | Title | Assigned to | Start | End | Days | Status | %Done | PM | [52 empty] | Item # | Task #
1 | Meetings | KOM | Kick off Meeting | PL | 2023-05-01 | 2023-05-12 | 1 | Complete | 100% | - | 2023-01-02: TRUE; 2023-05-08: u | 1 | Meetings
2 |  | C(E)-DRM-EV | Conceptual (Engineering) Design Review Meeting (Ex-Vessel) | PL | 2023-05-21 | 2023-06-21 | 1 | Complete | 100% | - | [52 empty] | 2 | bar: 2023-06-19
3 |  | C(E)-DRM-IV | Conceptual (Engineering) Design Review Meeting (In-Vessel) | PL | 2023-05-21 | 2023-06-22 | 1 | Complete | 100% | - | [52 empty] | 3 | bar: 2023-06-19
4 |  | C(E)-DRM-EV | Conceptual (Engineering) Design Review Meeting (Ex-Vessel) | PL | 2023-11-20 | 2023-12-20 | 1 | Not Started | 0% | - | [52 empty] | 4 | bar: 2023-12-18
5 |  | C(E)-DRM-IV | Conceptual (Engineering) Design Review Meeting (In-Vessel) | PL | 2023-11-20 | 2023-12-20 | 1 | Not Started | 0% | - | [52 empty] | 5 | bar: 2023-12-18
6 | 1 | 2023-THM-DIA-DMA-01 | Modeling and analysis activity | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 23.44% | 20.5 | [52 empty] | 6 | 1 | bar: 2023-12-18
7 |  | 2023-THM-DIA-DMA-01 (a) | Sensitivity analysis on misalignment of sensors | CREATE | 2023-01-02 | 2023-12-20 | 253 | In Progress | 70% | 1 | [52 empty] | 7 | bar: 2023-12-18
8 |  | 2023-THM-DIA-DMA-01 (b) | Sensitivity analysis on critical sensors | CREATE | 2023-01-02 | 2023-12-20 | 253 | In Progress | 70% | 1 | [52 empty] | 8 | bar: 2023-12-18
9 |  | 2023-THM-DIA-DMA-01 (c) | Sensitivity analysis on strike points reconstruction | CREATE | 2023-09-01 | 2023-10-01 | 21 | Not Started | 0% | 1 | [52 empty] | 9 | bar: 2023-09-25
10 |  | 2023-THM-DIA-DMA-01 (d) | Assessment of halo sensors number, position and sensitivity | CREATE | 2023-01-02 | 2023-12-20 | 253 | Blocked | 1% | 3.5 | [52 empty] | 10 |  | Use Disruption group results - Advice from Villone | bar: 2023-12-18
11 |  | 2023-THM-DIA-DMA-01 (e) | Assess Reconstruction capabilities during fast transient & main plasma scenarios time windows | CREATE | 2023-01-02 | 2023-12-20 | 253 | In Progress | 10% | 2 | [52 empty] | 11 | bar: 2023-12-18
12 |  | 2023-THM-DIA-DMA-01 (f) | Explore usage of saddle loops to design plasma centroid velocity estimator | CREATE | 2023-01-02 | 2023-11-06 | 221 | In Progress | 10% | 2 | [52 empty] | 12 | bar: 2023-11-06
13 |  | 2023-THM-DIA-DMA-01 (g) | Modal analysis using pick up coils | CREATE | 2023-01-02 | 2023-12-20 | 253 | Not Started | 0% | 1 | [52 empty] | 13 | bar: 2023-12-18
14 |  | 2023-THM-DIA-DMA-01 (h) | Optimization of number,position of bi-axial div. sensors for strike points reconstruction | CREATE | 2023-05-20 | 2023-09-01 | 75 | Not Started | 50% | 2 | [52 empty] | 14 | bar: 2023-08-28
15 |  | 2023-THM-DIA-DMA-01 (i) | FEM analysis on gradient temperatures and EM loads on sensors fixing plates | UNICA(2),LTCalcoli(5) | 2023-01-02 | 2023-12-20 | 253 | Not Started | 0% | 7 | [52 empty] | 15 | bar: 2023-12-18
16 | 2 | 2023-THM-DIA-DMA-02 | Hall sensors design | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 25% | 5 | [52 empty] | 16 | 2 | bar: 2023-12-18
17 |  | 2023-THM-DIA-DMA-02 (a) | Preliminary design of Ex-Vessel Hall sensor | CREATE(3) + IPP(2) | 2023-01-02 | 2023-12-20 | 253 | In Progress | 25% | 5 | [52 empty] | 17 | bar: 2023-12-18
18 |  |  | Identify impact on VV manifacturing |  | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | [53 empty] | 18 |  | * Preliminary fixating design with 1 boss (as per ITER ones) | bar: 2023-03-27
19 |  |  | FEM on Hall location and test on achoring method on VV |  | 2023-06-01 | 2023-12-20 | 145 | Not Started | 0% | [53 empty] | 19 | bar: 2023-12-18
20 |  |  | Manifacturing a prototype |  | 2023-12-01 | 2023-12-20 | 14 | Not Started | 0% | [53 empty] | 20 | bar: 2023-12-18
21 |  |  | Identify sensor routing and transmission line cable |  | 2023-10-01 | 2023-12-20 | 58 | Not Started | 0% | [53 empty] | 21 | bar: 2023-12-18
22 |  | 2023-THM-DIA-DMA-02 (b) | In-Vessel Hybrid Hall sensors proposal ???? | CREATE | 2023-01-02 | 2023-06-20 | 122 | In Progress | 0% | 0 | [52 empty] | 22 | bar: 2023-06-19
23 | 3 | 2023-THM-DIA-DMA-03 | Ex-vessel pick-up coils design | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 35% | 7 | [52 empty] | 23 | 3 | bar: 2023-12-18
24 |  | 2023-THM-DIA-DMA-03 (a) | Design proposal for the fixing plate sensor. Specify interface with VV manufacturing | RFX | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 2 | [52 empty] | 24 | bar: 2023-03-27
25 |  | 2023-THM-DIA-DMA-03 (b) | Manufacturing prototype of sensor and fixing plate + test on prototype | RFX | 2023-09-01 | 2023-12-20 | 79 | Not Started | 0% | 2 | [52 empty] | 25 | bar: 2023-12-18
26 |  | 2023-THM-DIA-DMA-03 (c) | Identify a local routing up to an intermediate connector collecting more sensors | RFX | 2023-07-01 | 2023-12-20 | 123 | Not Started | 0% | 2 | [52 empty] | 26 | bar: 2023-12-18
27 |  | 2023-THM-DIA-DMA-03 (d) | Final design of ex-vessel | RFX | 2023-01-02 | 2023-12-20 | 253 | In Progress | 40% | 1 | [52 empty] | 27 | bar: 2023-12-18
28 | 4 | 2023-THM-DIA-DMA-04 | In-vessel pick-up coils design | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 35% | 5.5 | [52 empty] | 28 | 4 | bar: 2023-12-18
29 |  | 2023-THM-DIA-DMA-04 (a) | Adopt the same design of ex-vessel fixing plate and estimate impact on VV manufacturing | RFX | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 1 | [52 empty] | 29 | bar: 2023-03-27
30 |  | 2023-THM-DIA-DMA-04 (b) | Manufacturing prototype of sensor and fixing plate. | RFX | 2023-10-01 | 2023-12-20 | 58 | Not Started | 0% | 2 | [52 empty] | 30 | bar: 2023-12-18
31 |  | 2023-THM-DIA-DMA-04 (c) | Identify a local routing up to an intermediate connector collecting more sensors | RFX | 2023-07-01 | 2023-12-20 | 123 | Not Started | 0% | 1.5 | [52 empty] | 31 | bar: 2023-12-18
32 |  | 2023-THM-DIA-DMA-04 (d) | Final design of in-vessel | RFX | 2023-01-02 | 2023-12-20 | 253 | In Progress | 40% | 1 | [52 empty] | 32 | bar: 2023-12-18
33 | 5 | 2023-THM-DIA-DMA-05 | In-vessel high frequency printed sensors final design | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 40% | 5.5 | [52 empty] | 33 | 5 | IDENTIFY routing and transmission line type (non specified in the call - could be done within task #12 | bar: 2023-12-18
34 |  | 2023-THM-DIA-DMA-05 (a) | Solve existing design issues and Specify interface with VV manufacturing | EPFL | 2023-01-02 | 2023-12-20 | 253 | In Progress | 50% | 3 | [52 empty] | 34 |  | Possible rollover on LTCC design - Adopted same criteria for In vessel PU coils | bar: 2023-12-18
35 |  | 2023-THM-DIA-DMA-05 (b) | Manufacturing of sensor prototype and fixing plate. | EPFL | 2023-01-02 | 2023-12-20 | 253 | In Progress | 60% | 2 | [52 empty] | 35 | bar: 2023-12-18
36 |  | 2023-THM-DIA-DMA-05 (c) | Testing to be agreed | EPFL | 2023-05-01 | 2023-12-20 | 168 | In Progress | 10% | 0.5 | [52 empty] | 36 | bar: 2023-12-18
37 | 6 | 2023-THM-DIA-DMA-06 | Final design of Flux Loops | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 42.5% | 2.5 | [52 empty] | 37 | 6 | bar: 2023-12-18
38 |  | 2023-THM-DIA-DMA-06 (a) | Specify interface with VV manufacturing | ENEA + CETMA(0.5) | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 0.5 | [52 empty] | 38 | bar: 2023-03-27
39 |  | 2023-THM-DIA-DMA-06 (b) | Design Sensor | ENEA | 2023-01-02 | 2023-12-20 | 253 | In Progress | 70% | 0.5 | [52 empty] | 39 | bar: 2023-12-18
40 |  | 2023-THM-DIA-DMA-06 (c) | Manufacturing of sensor prototype | ENEA | 2023-10-01 | 2023-12-20 | 58 | Not Started | 0% | 1 | [52 empty] | 40 | bar: 2023-12-18
41 |  | 2023-THM-DIA-DMA-06 (d) | Identify routing for all sensors and transmission line type | CETMA | 2023-07-01 | 2023-12-20 | 123 | Not Started | 0% | 0.5 | [52 empty] | 41 | bar: 2023-12-18
42 | 7 | 2023-THM-DIA-DMA-07 | Final design of Saddle loops | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 40% | 2.5 | [52 empty] | 42 | 7 | bar: 2023-12-18
43 |  | 2023-THM-DIA-DMA-07 (a) | Specify interface with VV manufacturing | ENEA + CETMA(0.5) | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 0.5 | [52 empty] | 43 | bar: 2023-03-27
44 |  | 2023-THM-DIA-DMA-07 (b) | Design Sensor | ENEA | 2023-01-02 | 2023-12-20 | 253 | In Progress | 60% | 0.5 | [52 empty] | 44 | bar: 2023-12-18
45 |  | 2023-THM-DIA-DMA-07 (c) | Manufacturing of sensor prototype | ENEA (0.5) + CETEMA(0.5) | 2023-11-01 | 2023-12-20 | 36 | Not Started | 0% | 1 | [52 empty] | 45 | bar: 2023-12-18
46 |  | 2023-THM-DIA-DMA-07 (d) | Identify routing for all sensors and transmission line type | CETMA | 2023-08-01 | 2023-12-20 | 102 | Not Started | 0% | 0.5 | [52 empty] | 46 | bar: 2023-12-18
47 | 8 | 2023-THM-DIA-DMA-08 | Preliminary design of Diamagnetic loops | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 32.5% | 3 | [52 empty] | 47 | 8 | bar: 2023-12-18
48 |  | 2023-THM-DIA-DMA-08 (a) | Specify interface with VV manufacturing | ENEA + CETMA(0.5) | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 0.5 | [52 empty] | 48 | bar: 2023-03-27
49 |  | 2023-THM-DIA-DMA-08 (b) | Design Sensor | ENEA | 2023-01-02 | 2023-12-20 | 253 | In Progress | 30% | 1 | [52 empty] | 49 | bar: 2023-12-18
50 |  | 2023-THM-DIA-DMA-08 (c) | Manufacturing of sensor prototype | ENEA (0.5) + CETEMA(0.5) | 2023-12-01 | 2023-12-20 | 14 | Not Started | 0% | 1 | [52 empty] | 50 | bar: 2023-12-18
51 |  | 2023-THM-DIA-DMA-08 (d) | Identify routing for all sensors and transmission line type | CETMA | 2023-09-01 | 2023-12-20 | 79 | Not Started | 0% | 0.5 | [52 empty] | 51 | bar: 2023-12-18
52 | 9 | 2023-THM-DIA-DMA-09 | Preliminary Design of Rogowski coils and compensation loop | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 30% | 3 | [52 empty] | 52 | 9 | bar: 2023-12-18
53 |  | 2023-THM-DIA-DMA-09 (a) | Specify interface with VV manufacturing | ENEA + CETMA(0.5) | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 0.5 | [52 empty] | 53 | bar: 2023-03-27
54 |  | 2023-THM-DIA-DMA-09 (b) | Design Sensor | ENEA | 2023-01-02 | 2023-12-20 | 253 | In Progress | 20% | 1 | [52 empty] | 54 | bar: 2023-12-18
55 |  | 2023-THM-DIA-DMA-09 (c) | Manufacturing of sensor prototype | ENEA (0.5) + CETEMA(0.5) | 2023-12-01 | 2023-12-20 | 14 | Not Started | 0% | 1 | [52 empty] | 55 | bar: 2023-12-18
56 |  | 2023-THM-DIA-DMA-09 (d) | Identify routing for all sensors and transmission line type | CETMA | 2023-10-01 | 2023-12-20 | 58 | Not Started | 0% | 0.5 | [52 empty] | 56 | bar: 2023-12-18
57 | 10 | 2023-THM-DIA-DMA-10 | Preliminary design of Fiber optic current sensor | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 27.75% | 3 | [52 empty] | 57 | 10 | bar: 2023-12-18
58 |  | 2023-THM-DIA-DMA-10 (a) | Specify interface with VV manufacturing | ENEA + CETMA(0.5) | 2023-01-02 | 2023-04-01 | 65 | Complete | 100% | 0.5 | [52 empty] | 58 | bar: 2023-03-27
59 |  | 2023-THM-DIA-DMA-10 (b) | Design Sensor | ENEA | 2023-01-02 | 2023-12-20 | 253 | In Progress | 10% | 1 | [52 empty] | 59 | bar: 2023-12-18
60 |  | 2023-THM-DIA-DMA-10 (c) | Manufacturing of sensor prototype | ENEA (0.5) + CETEMA(0.5) | 2023-12-01 | 2023-12-20 | 14 | Blocked | 1% | 1 | [52 empty] | 60 | bar: 2023-12-18
61 |  | 2023-THM-DIA-DMA-10 (d) | Identify routing for all sensors and transmission line type | CETMA | 2023-11-01 | 2023-12-20 | 36 | Not Started | 0% | 0.5 | [52 empty] | 61 | bar: 2023-12-18
62 | 11 | 2023-THM-DIA-DMA-11 | CDA of data acquisition system | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 12.5% | 3 | [52 empty] | 62 | 11 | bar: 2023-12-18
63 |  | 2023-THM-DIA-DMA-11 (a) | Estimate nr of signals | ENEA | 2023-01-02 | 2023-06-20 | 122 | In Progress | 50% | 0.5 | [52 empty] | 63 | bar: 2023-06-19
64 |  | 2023-THM-DIA-DMA-11 (b) | Surwey of requirements for each type of sensors | ENEA | 2023-07-01 | 2023-10-01 | 65 | Not Started | 0% | 1 | [52 empty] | 64 | bar: 2023-09-25
65 |  | 2023-THM-DIA-DMA-11 (c) | Adapt the analogic front-end of Hardware concept selected by CODAS | ENEA | 2023-11-01 | 2023-12-20 | 36 | Not Started | 0% | 1 | [52 empty] | 65 | bar: 2023-12-18
66 |  | 2023-THM-DIA-DMA-11 (d) | Test on protptypes | ENEA | 2023-12-01 | 2023-12-20 | 14 | Not Started | 0% | 0.5 | [52 empty] | 66 | bar: 2023-12-18
67 | 12 | 2023-THM-DIA-DMA-12 | CDA of coils placement cabling and connection in VV and cryostat | - | 2023-01-02 | 2023-12-20 | 253 | Not Started | 0% | 2 | [52 empty] | 67 | 12 | bar: 2023-12-18
68 |  | 2023-THM-DIA-DMA-10 (a) | Determine the number and size of cables needed for each sub-system | ENEA | 2023-06-01 | 2023-06-30 | 22 | Not Started | 0% | 0.5 | [52 empty] | 68 | bar: 2023-06-26
69 |  | 2023-THM-DIA-DMA-10 (b) | Group cable bundles according to vessel/cryostat nearest available exit | ENEA | 2023-07-01 | 2023-07-30 | 20 | Not Started | 0% | 0.5 | [52 empty] | 69 | bar: 2023-07-24
70 |  | 2023-THM-DIA-DMA-10 (c) | Determine the cable path and size of cable conduits | CETMA | 2023-07-01 | 2023-10-01 | 65 | Not Started | 0% | 0.5 | [52 empty] | 70 | bar: 2023-09-25
71 |  | 2023-THM-DIA-DMA-10 (d) | Conceptual design of cable conduit | CETMA | 2023-07-01 | 2023-11-01 | 88 | Not Started | 0% | 0.25 | [52 empty] | 71 | bar: 2023-10-30
72 |  | 2023-THM-DIA-DMA-10 (e) | Insert conduits approximate size in VV CAD drawing | CETMA | 2023-11-01 | 2023-12-01 | 23 | Not Started | 0% | 0.25 | [52 empty] | 72 | bar: 2023-11-27
73 | 13 | 2023-THM-DIA-DMA-13 | Assessment of measurement performance for high-frequency modes | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 50% | 2 | [52 empty] | 73 | 13 |  | see report previous year | bar: 2023-12-18
74 |  | 2023-THM-DIA-DMA-13 | Assess optimal high bandwidth sensors number and position | ENEA(1) + EPFL(1) | 2023-01-02 | 2023-12-20 | 253 | In Progress | 50% | 2 | [52 empty] | 74 | bar: 2023-12-18
75 | 14 | 2023-THM-DIA-DMA-14 | CAD drawings and integration | - | 2023-01-02 | 2023-12-20 | 253 | In Progress | 25% | 6 | [52 empty] | 75 | 14 | bar: 2023-12-18
76 |  | 2023-THM-DIA-DMA-14 (a) | Integration of designed magnetic sensors in the main DTT CATIA model. | ENEA(1) + PROMECH(2) | 2023-01-02 | 2023-12-20 | 253 | In Progress | 50% | 3 | [52 empty] | 76 |  | Include EX Halls,EX Toroidal Pick UP, In vessel Pronted Sensors, Div Sensors….. | bar: 2023-12-18
77 |  | 2023-THM-DIA-DMA-14 (b) | Draw cabling paths and connections in VV and Cryostat and integration in the main DTT CATIA model | ENEA(1) + PROMECH(2) | 2023-09-01 | 2023-12-20 | 79 | Not Started | 0% | 3 | [52 empty] | 77 | bar: 2023-12-18
78 | 15 | 2023-THM-DIA-DMA-15 | Preliminary design of divertor cassette coils | - | 2023-01-02 | 2023-12-20 | 253 | Not Started | 0% | 1 | [52 empty] | 78 | 15 | bar: 2023-12-18
79 |  | 2023-THM-DIA-DMA-15 | Provide a preliminary design of bi-axial pick-up coils to be mounted on the divertor cassette | ENEA | 2023-01-02 | 2023-12-20 | 253 | Not Started | 0% | 1 | [52 empty] | 79 |  | assign to who to design the divertor coils?????? | bar: 2023-12-18
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))

## Status
Not Started
In Progress
Blocked
Complete
FORMULE
| today | Formula->
| bars | Formula-> | TRUE
| %complete | Formula-> | FALSE
| complete | Formula-> | FALSE
| blocked bar | Formula-> | FALSE